## Example
Project Name | Mimic
Project Description | A small, IRC-like chat client with native server capabilities. Only to work on the local network.
Modules | Milestone | Due Date | Goal % Complete | Actual % Complete | 2020-01-17
I. Server (Low-Level) | 1. Create basic socket server | 2020-01-17 | 50% | 100% | 2020-01-24
|  | 2020-01-24 | 100% | 100%
| 2. Write main loop waiting for connections | 2020-01-31 | 100% | 100% | 2020-01-31
| 3. Write Thread class to handle each client | 2020-02-07 | 33% | 70% | 2020-02-07
|  | 2020-02-14 | 77% | 90%
|  | 2020-02-21 | 100% | 100%
| 4. Determine format of packets sent to/from server | 2020-02-28 | 100% | 100%* | 2020-02-14
| 5. Create system to communicate messages between threads | 2020-03-06 | 100% | 100%* | 2020-02-21
| 6. Create way to read config file | 2020-03-13 | 100% | 100% | 2020-02-28
II. Client (Low-Level) | 1. Create basic socket client | 2020-03-13 | 100% | 100%** | 2020-03-06
| 2. Create set of methods for driver/GUI use | 2020-03-27 | 100% | 100% | 2020-03-13
| 3. Parse messages from server | 2020-04-03 | 100% | 100% | March 20 is a holiday | Week of Spring Break
| 4. Create network scanning functionality | 2020-04-14 | 100% | 100% | 2020-03-27
III. Client GUI | 1. Handle passed server flags to connect automatically | 2020-04-14 | 70% | 100% | 2020-04-03
| 2. Offer access to network scanning/server discovery and manual IP entering | 2020-04-14 | 60% | 100% | April 10 is a holiday | April 13 - Monday after
| 3. Start the client and connect | 2020-04-14 | 50% | 100% | 2020-04-17
| All 3 above | 2020-04-17 | 100% | 100% | 2020-04-24
| 4. Prompt for onscreen name on connection | 2020-04-24 | 100% | 100% | 2020-05-01
| 5. Create chat environment | 2020-04-24 | 50% | 100% | 2020-05-08
|  | 2020-05-01 | 100% | 100% | 2020-05-15
| a. Draw base chat environment based on config from server | 2020-04-24 | 100% | 100% | 5/19/2020 - last day
| b. Interact with client to send messages and display received messages | 2020-05-01 | 100% | 100%
| 6. Convert to JavaFX | 2020-05-01 | 100% | 100%
IV. Server GUI | 1. Allow user to choose configuration file | 2020-05-08 | 100% | 100%
| 2. Start the server | 2020-05-08 | 100% | 100%
| 3. Close GUI and start client GUI with server flags set | 2020-05-08 | 100% | 100%
V. Main GUI | 1. Allow user to choose either server or client | 2020-05-08 | 100% | 100%
| 2. Close GUI and start the specified GUI | 2020-05-08 | 100% | 100%
VI. Finishing Touches | 1. Optional: package into JAR/executable | 2020-05-15 | 100% | 100%
| 2. TBD | 2020-05-15 | 100% | 100%
VII. Presentation | 1. Create presentation | 2020-05-22 | 100% | 100%
| 2. Create video | 2020-05-22 | 100% | 100%
* = somewhat needed for writing the Thread class, hence the going out of order
** = only wrote basic one for testing server
video = demonstration of finished product
presentation = documentation
- initial goals
- struggles
- adjustments necessary
- expected things you learned
- surprising things you learned
Formulas:
Due Date = [Due Date, row above] + 7
Due Date = [Due Date, row above]